## Charter
PROJECT DESCRIPTION
The LUXE NEST Website Development Project aims to design and launch a high-quality, user-centric website showcasing premium interior design services, focusing on bedroom and living room spaces. The project involves front-end and back-end development, UI/UX design, content creation, SEO optimization, booking system integration, and marketing launch. It will serve as a digital brand identity and client engagement platform, enabling lead generation and service inquiries.
BUSINESS NEED
LUXE NEST requires a robust digital presence to expand its reach, establish credibility, and convert online traffic into leads. The business needs a responsive, SEO-optimized platform that reflects the brand’s premium offerings, provides seamless customer interaction, and supports marketing efforts. This initiative supports the broader goal of increasing visibility, improving customer experience, and driving revenue growth through digital channels.
OWNERSHIP & APPROVAL
Project Manager | Gezatan Nimal Raj |  | Project Champion | Tanushree Raja |  | Approval Date | Pending
Project Number | PRJ001
FINANCIALS & MILESTONES
Financials |  |  | Capital/Expense |  |  | Milestones (Schedule)
| Goal | Actual |  | Goal | Actual |  | Goal | Actual
Initial Investment | 2022000 |  | Website Development (Front end, Back end) | 600000 |  | Requirements gathering | 2024-11-10
Net Present Value (5 yr) | 3898573.7174 |  | UI/ UX Design | 200000 |  | Development | 2024-11-20
ROI | 15.22% |  | Content Creation | 150000 |  | Testing | 2025-01-20
IRR | 18.57% |  | SEO Setup and initial optimzation | 100000 |  | Training and Documentation | 2025-02-07
|  |  | Hosting and cloud setup (1st year) | 75000 |  | Go-Live | 2025-02-14
|  |  | Booking and Inquiry system integration | 250000 |  | Post Integration Evaluation | 2025-02-28
|  |  | Digital branding and identity design | 125000
|  |  | Testing & quality assurance | 75000
| Capital |  | Training & documentation | 50000
| Expenses |  | Contingency (Buffer ~5%) | 75000
|  |  | Marketing Strategy & launch campaign | 200000
|  |  | Photography and visual assets | 100000
RESOURCES & RISKS
Internal Resources |  |  | External Services |  |  | Project Risks
| Total Hours | Peak Hrs/Wk |  | Budget | Actual |  | Medium | High
Stephen (Developer) | 520 | 40 | Website hosting (AWS, Hostinger) | 75000 |  | Scope creep | ü
Tamil Selvan (Developer) | 520 | 40 | Domain Registration | 2000 |  | Delays In content | ü
Godfrey Morris (Developer) | 520 | 40 | UI/ UX Designer (Freelancer) | 200000 |  | Budget Overrun |  | ü
Bebito Clements (Developer) | 520 | 40 | SEO & Content writing Services (Agency) | 150000 |  | Vendor Dependency |  | ü
Juliya (Solution Architect) | 250 | 20 | Photography/ 3D Renders | 100000 |  | Technical issues post launch |  | ü
Christopher (QA Tester) | 320 | 30 | Marketing Consultant | 200000
Benita (QA Tester) | 320 | 30 | Legal & policy documentation | 10000
Dawood (Trainer) | 160 | 20 | Analytics Setup (Google Analytics, Heatmaps) | 10000
Kuberan Ravi (Finance Analyst) | 100 | 10
Vishnu (Business Analyst) | 200 | 15

## Financials
Financial Benefits and Costs
Note - review with your finance team to ensure accurate assumptions and calculations
Cost of Capital | 8% | (see finance team for updated value)
Initial Cost of Project | 2022000
Cash Inflows | Year | 0 | 1 | 2 | 3 | 4 | 5
Incremental Revenue * Margin |  |  | 900000 | 900000 | 900000 | 900000 | 900000
Material Cost Savings |  |  | 100000 | 100000 | 100000 | 100000 | 100000
Labor Savings |  |  | 50000 | 50000 | 50000 | 50000 | 50000
Other Savings - Warranty |  |  | 25000 | 25000 | 25000 | 25000 | 25000
Other |  |  | 50000 | 50000 | 50000 | 50000 | 50000
Cash Inflow |  |  | 1125000 | 1125000 | 1125000 | 1125000 | 1125000
Present Value of Cash Inflow |  |  | 1041666.6667 | 964506.1728 | 893061.2711 | 826908.5844 | 765656.0967
Cumulative Cash Inflow |  |  | 1041666.6667 | 2006172.8395 | 2899234.1107 | 3726142.695 | 4491798.7917
Costs
Initial Investment |  | 2022000
Equipment Service Contract |  |  | 100000 | 100000 | 100000 | 100000 | 100000
Incremental Data Storage |  |  | 50000 | 50000 | 50000 | 50000 | 50000
Equipment Lease |  |  | 120000 | 120000 | 120000 | 120000 | 120000
Other |  |  | 200000 | 200000 | 200000 | 200000 | 200000
Cash Outflow |  | 2022000 | 470000 | 470000 | 470000 | 470000 | 470000
PV of Cash Outflow |  | 2022000 | 435185.1852 | 402949.2455 | 373101.1533 | 345464.0308 | 319874.1026
Cumulative Cash Outflow |  | 2022000 | 2457185.1852 | 2860134.4307 | 3233235.584 | 3578699.6148 | 3898573.7174
NPV of Project | 593225.0743
IRR | 18.57%
ROI | 15.22%
Year |  | 0 | 1 | 2 | 3 | 4 | 5
Cash Flow |  | -2022000 | 655000 | 655000 | 655000 | 655000 | 655000